## Run of Show
EVENT DAY TIMELINE · RUN OF SHOW
The Diary of an Event Girl · Fill in each row, share with your team and key vendors, and event day runs itself.
EVENT |  |  |  | DATE |  | VENUE
Time | Duration | Phase | What Happens | Who Leads | Vendor / Support | Status | Notes
7:00 AM | 2 hrs | Setup | Team arrives, venue walkthrough, mark out zones | Lead Planner | Venue | Done | Confirm power points and access
9:00 AM | 2 hrs | Setup | Decor and staging setup begins | Styling Lead | Decorator | Done | Backdrop first, then tables
11:00 AM | 1 hr | Vendor Arrivals | Catering, sound, and lighting load in | Coordinator | Caterer, DJ | In progress | Stagger arrivals to avoid clash
12:00 PM | 30 min | Team Briefing | Full team walkthrough and final brief | Lead Planner | All crew | To do | Hand out printed timelines
1:00 PM | 1 hr | Final Checks | Sound check, lighting test, table settings | Coordinator | DJ, Lighting | To do | Test mics and playlist
2:00 PM | 30 min | Doors Open | Guest arrival, registration, welcome drinks | Guest Team | Ushers, Bar | To do | Greeters at entrance
2:30 PM | 45 min | Programme | Welcome and opening remarks | MC | Sound | To do | MC has running order
3:15 PM | 1 hr | Meal / Service | Lunch service begins | Catering Lead | Caterer | To do | Watch dietary tables
4:15 PM | 45 min | Key Moment | Main event moment (speech, cake, reveal) | Lead Planner | Photo, Sound | To do | Cue photographer early
5:00 PM | 1 hr | Programme | Entertainment and guest activities | MC | DJ | To do | Keep energy up
6:00 PM | 45 min | Close | Closing remarks, thank yous, send-off | MC | Sound | To do | Prepare send-off items
6:45 PM | 1.5 hrs | Breakdown | Guest departure, vendor breakdown, collection | Coordinator | All vendors | To do | Check for lost property
Note on A7: This is a sample run of show. Edit every row to match your event, or clear it and start fresh.

## How to Use
HOW TO USE YOUR RUN OF SHOW
1. Fill in your event name, date, and venue at the top of the Run of Show tab.
2. The sheet comes pre-filled with a realistic sample day. Edit each row to match your event, or clear it and build your own.
3. Work in order of time. Every row is one moment: when it happens, how long it takes, who leads it, and which vendor supports it.
4. Use the Phase and Status dropdowns to keep it consistent and easy to scan.
5. As the day progresses, update Status. Done turns green, In progress turns amber.
6. Print it or share it with your whole team and key vendors before the event. When everyone works from the same timeline, you lead instead of chase.
A good run of show is the single most powerful document on event day. Keep it in front of you, and nothing surprises you.